CREATIVE & PRODUCTION BRIEF

# BEYOND TENUN - SEED TO LOOM

TBN Conference 2026

24-25 September 2026

| ICM | TBN | TORAJAMELO |
| --- | --- | --- |

HERO PROGRAM Beyond Tenun - Seed to Loom is the hero program. ICM × TBN × Torajamelo is the collaborative ecosystem behind it. Local communities are the center.

Funding ambition: USD 1,000,000 / 3 years

Main narrative

Humanizing Artificial Intelligence through Ancestral Intelligence

From local resilience to human flourishing.

# 1. Assignment Context

Impact Creative Management (ICM), Transformational Business Network (TBN) and Torajamelo have agreed to collaborate on one pilot program, Beyond Tenun - Seed to Loom, focused on communities in Adonara, Lembata and Manggarai. The partnership intends to use TBN Conference 2026 as a strategic moment to attract serious funding partners for a three-year program and to introduce the ICM ecosystem through a real collaborative case.

PRIMARY OBJECTIVE Create a coherent set of conference materials that helps potential investors, donors, foundations, grant makers and strategic partners understand, remember and engage with Beyond Tenun - and move into a meaningful follow-up conversation.

# 2. Communication Hierarchy

| Priority | What the audience should understand |
| --- | --- |
| 1. HERO | Beyond Tenun - Seed to Loom is the concrete program and funding opportunity. |
| 2. ECOSYSTEM | ICM × TBN × Torajamelo combine complementary capabilities to make the program possible. |
| 3. CENTER | Local communities, local knowledge, women and local institutions remain at the center. |
| 4. VISION | Humanizing AI through Ancestral Intelligence, ultimately contributing to human flourishing. |
| 5. CTA | Join the three-year journey as an Impact Partner / funding partner / strategic collaborator. |

# 3. Conference Conversion Goal

1. NOTICE - make the booth and materials visually strong enough to stop the right people.

2. UNDERSTAND - explain Beyond Tenun simply within 2-3 minutes.

3. BELIEVE - show credible program logic, collaboration and real community grounding.

4. ENGAGE - create reasons for investors/funders to ask questions and spend time with the team.

5. CONTINUE - capture interest and move qualified contacts into follow-up meetings after the conference.

# 4. Deliverables Overview

| # | Deliverable | Primary Use | Priority |
| --- | --- | --- | --- |
| 1 | Master Key Visual & Message System | All conference materials | CORE |
| 2 | Main Investor / Impact Partner Pitch Deck | 10-15 minute meetings/pitches | CORE |
| 3 | Short Investor / Conversation Deck | 5-7 minute conversations | CORE |
| 4 | Beyond Tenun Pitch Video | Booth, pitch opener, investor follow-up | CORE |
| 5 | ICM Ecosystem Launch / Profile Video | Introduce collaboration ecosystem | CORE |
| 6 | Beyond Tenun Executive One-Pager | Fast handout / WhatsApp follow-up | CORE |
| 7 | Impact Partnership / Funding One-Pager | Explain the USD 1M ask clearly | CORE |
| 8 | Booth Master Visual & Environmental Design | Exhibition presence | CORE |
| 9 | Booth Screen Content Loop | Silent visual attraction | CORE |
| 10 | Traceable Weaver Experience / Prototype | Tangible technology demo | CORE |
| 11 | Leaders Roundtable Kit | Invitation-only side event | TEMPLATE-BASED |
| 12 | Kim Tan / Key Leader Executive Brief | High-level one-on-one conversation | TEMPLATE-BASED |
| 13 | Lead Capture / QR Experience | Capture qualified interest | TEMPLATE-BASED |
| 14 | Post-Conference Follow-Up Pack | Convert leads after conference | TEMPLATE-BASED |

BUDGET DISCIPLINE With an IDR 12M budget, the agency should build one strong visual/message system and reuse it intelligently. Do not create fourteen disconnected creative directions.

# 5.1. Master Key Visual & Message System

Purpose: Create one coherent conference identity for Beyond Tenun so that every deck, video, booth panel, one-pager and invitation feels like one strategic campaign.

## Agency to deliver

- One master key visual direction

- Headline + sub-headline hierarchy

- Typography and color direction

- Photo treatment and graphic language

- Icon / diagram style

- CTA language

- Logo lock-up / partnership treatment for ICM × TBN × Torajamelo

- Mini application guide for all conference assets

## Content / message direction

- Hero: BEYOND TENUN - SEED TO LOOM

- Narrative: Humanizing Artificial Intelligence through Ancestral Intelligence

- Destination: From local resilience to human flourishing

- CTA: Join the 3-Year Journey / Become an Impact Partner

## Format / production notes

- Design should feel premium, intelligent, human and rooted in Indonesian/local culture without becoming decorative or folkloric.

## Where it will be used

- Applied consistently across all print and digital materials

- All final files plus editable source files

IMPORTANT Do not position one organization as the owner/boss of the other two. The collaboration should feel equal; local communities must remain visually and narratively central.

# 5.2. Main Investor / Impact Partner Pitch Deck

Purpose: Support a structured 10-15 minute pitch to serious potential funders and partners.

## Agency to deliver

- Investor-ready deck, approximately 10-12 slides

- Editable PowerPoint source

- PDF version for sharing

## Content / message direction

- The human problem: disaster, disrupted livelihoods, women’s vulnerability and knowledge loss

- What is being lost: Ancestral Intelligence

- The thesis: Humanizing AI

- Beyond Tenun / Seed to Loom as the living case

- Program architecture: Seed to Loom + Traceable Weavers + Future Education + Climate Action Beyond Carbon + Local Impact Hub

- Collaboration ecosystem: ICM × TBN × Torajamelo + local communities

- Three-year journey: Restore → Regenerate → Flourish

- Impact outcomes

- USD 1M / 3 years funding ambition

- Clear invitation to continue the conversation / become an Impact Partner

## Format / production notes

- Use strong visual hierarchy and simple diagrams rather than dense paragraphs

- Agency to polish and visualize approved content, not invent unsupported claims or impact numbers

## Where it will be used

- Investor meetings

- Formal conference pitch opportunities

- Private partner conversations

- Post-conference follow-up

IMPORTANT The deck should make the funding opportunity feel structured and serious, not like crowdfunding.

# 5.3. Short Investor / Conversation Deck

Purpose: Enable a strong pitch when the team has only 5-7 minutes with a potential partner.

## Agency to deliver

- Short deck, maximum 5-6 slides

- Editable PPT and PDF

## Content / message direction

- Why this matters

- What Beyond Tenun is

- How the ecosystem works

- Three-year journey and expected change

- USD 1M opportunity

- Invitation / next step

## Format / production notes

- Should stand alone without needing the full deck

- Strong enough to send by WhatsApp after a short conversation

## Where it will be used

- Booth conversations

- Quick investor introductions

- Coffee-break meetings

- Follow-up message after meeting

IMPORTANT This is not simply a shortened full deck. It should be designed specifically for fast decision-maker conversations.

# 5.4. Beyond Tenun Pitch Video

Purpose: Create an emotional and strategic entry point that makes people understand why Beyond Tenun matters before they see the detailed program.

## Agency to deliver

- One 90-120 second hero pitch video

- 16:9 presentation version

- Optimized compressed version for WhatsApp/email

- Editable project file or agreed source package where possible

## Content / message direction

- Open with the human problem, not logos

- Show disruption but avoid exploiting trauma

- Move into the intelligence and capacity that already exist in communities

- Introduce Seed to Loom as revival and strengthening

- Introduce technology / Traceable Weavers as an amplifier of ancestral intelligence

- Connect education, climate resilience and Local Impact Hub

- End with the 3-year impact partnership and USD 1M funding ambition

- Final CTA: Join the Journey

## Format / production notes

- Must work with voiceover or captions

- Prefer subtitles so the video remains understandable in a conference environment

- Use supplied or properly licensed footage/images only

## Where it will be used

- Booth screen

- Pitch opening

- Leaders Roundtable opening

- Private investor meeting

- Post-conference follow-up

IMPORTANT Tone: cinematic, human, hopeful, premium and intelligent. Avoid generic corporate stock-video style.

# 5.5. ICM Ecosystem Launch / Profile Video

Purpose: Introduce ICM’s repositioning and explain how the ICM ecosystem enables collaborations such as Beyond Tenun.

## Agency to deliver

- One 60-90 second profile / launch video

- 16:9 version

- Compressed digital-sharing version

## Content / message direction

- Opening thought: complex problems cannot be solved by one organization alone

- ICM as Catalyst & Program Orchestrator

- ICM as Knowledge Lab & Amplifying

- ICM connects people, ideas, knowledge and opportunities

- Beyond Tenun shown as one concrete example of the ICM ecosystem in action

- ICM × TBN × Torajamelo shown as complementary partners

## Format / production notes

- Clean motion graphics and consistent conference visual system

- Avoid long company history or service catalogue

## Where it will be used

- Booth

- Side meetings

- ICM ecosystem introduction

- Post-conference partner sharing

IMPORTANT This video supports Beyond Tenun. It should not compete with the hero program or turn the conference into an ICM corporate launch event.

# 5.6. Beyond Tenun Executive One-Pager

Purpose: Provide a fast, premium document for someone who says: “Send me something.”

## Agency to deliver

- One-page or maximum two-page executive brief

- Print-ready PDF

- Lightweight digital PDF

## Content / message direction

- The challenge

- The big idea / why now

- What Beyond Tenun builds

- Geographic focus: Adonara, Lembata, Manggarai

- Three-year journey

- Expected impact areas

- Funding ambition: USD 1M / 3 years

- Who is collaborating

- Simple CTA / contact

## Format / production notes

- Premium design with strong white space

- Readable within 2-3 minutes

## Where it will be used

- Booth handout

- Investor follow-up

- Kim Tan / leader follow-up

- WhatsApp / email attachment

# 5.7. Impact Partnership / Funding One-Pager

Purpose: Answer clearly: “What exactly are you asking from us?”

## Agency to deliver

- One dedicated funding / partnership one-pager

- Print-ready and digital PDF

## Content / message direction

- USD 1,000,000 total ambition over 3 years

- Positioning as a small consortium of committed Impact Partners, not crowdfunding

- Possible forms of support: grants, philanthropic capital, catalytic capital, corporate/foundation funding, strategic/in-kind partnership; separate investment instruments only where financial-return vehicles actually exist

- High-level funding categories: community capacity, Seed to Loom, technology/traceability, education, climate/regeneration, Local Impact Hub, measurement/knowledge

- What partners receive: transparency, learning, evidence, engagement and relationship - not operational control

## Format / production notes

- Simple, high-level and credible; detailed budget lives elsewhere

## Where it will be used

- Investor meetings

- Foundation/grant conversations

- Booth handout

- Follow-up pack

# 5.8. Booth Master Visual & Environmental Design

Purpose: Turn the booth into a conversation starter and investor engagement point, not a static company-profile display.

## Agency to deliver

- Main backdrop / hero wall artwork (not mandatory)

- Program journey panel

- ICM × TBN × Torajamelo ecosystem panel

- Funding / CTA panel

- QR signage

- Basic application mockup of booth environment

- Print-ready production files with dimensions adaptable to final booth specs

## Content / message direction

- Suggested hero: AI IS BECOMING MORE INTELLIGENT. ARE WE BECOMING WISER?

- BEYOND TENUN - Humanizing AI through Ancestral Intelligence

- Program pathway: Seed → Loom → Traceable Weavers → Education → Climate → Local Impact Hub → Human Flourishing

- Ecosystem: three equal collaborators around Local Community

- CTA: Join the 3-Year Journey / USD 1M Impact Partnership

## Format / production notes

- Keep text minimal; booth should work at a glance from several meters away

- Use physical product / textile / story element where available

## Where it will be used

- Exhibition booth throughout TBN Conference

IMPORTANT Do not fill the booth with company profile text. Every surface should either attract, explain, demonstrate or invite conversation.

# 5.9. Booth Screen Content Loop

Purpose: Keep the booth communicating even when staff are talking to other visitors.

## Agency to deliver

- One silent/semi-silent loop, approximately 3-5 minutes

- 16:9 HD export

- Editable source or agreed project handover

## Content / message direction

- Short message sequence: AI question → community reality → Beyond Tenun → Seed to Loom → Traceable Weaver → Education → Climate → Local Impact Hub → collaboration ecosystem → USD 1M / 3 years → QR CTA

- Mix selected motion graphics, photography and key statements

- End and restart seamlessly

## Format / production notes

- Must be understandable without audio

- Large text suitable for viewing from a distance

- Avoid dense charts

## Where it will be used

- TV / monitor at booth

# 5.10. Traceable Weaver Experience / Prototype

Purpose: Make the technology layer tangible so investors can immediately understand how technology can amplify, not replace, ancestral intelligence.

## Agency to deliver

- One interactive/mock digital prototype linked from a QR code

- One sample printed QR tag / card for a textile or product

- Simple mobile page / prototype screens

## Content / message direction

- Meet the Weaver

- Community / place

- Material

- Technique

- Motif / cultural story

- Seed-to-Loom journey

- Impact / community benefit

- Optional market/product link

## Format / production notes

- Prototype/demo only - not a full software platform

- Use clearly marked sample/demo content where real consent/data is not yet available

## Where it will be used

- Booth demonstration

- Investor conversation

- Pitch / roundtable supporting example

IMPORTANT Do not publish personal or cultural information without appropriate consent. This deliverable demonstrates the experience concept, not a final data platform.

# 5.11. Leaders Roundtable Kit

Purpose: Support a small invitation-only side event that positions Beyond Tenun as a strategic conversation about Humanizing AI, Ancestral Intelligence and Human Flourishing.

## Agency to deliver

- Premium digital invitation

- One-page concept note

- Simple agenda

- Opening deck, maximum 4-5 slides

- Optional name cards / table tents template

## Content / message direction

- Proposed title: Humanizing AI - What Can Ancestral Intelligence Teach Us About Human Flourishing?

- The paradox of AI and human wisdom

- Brokenness / vulnerability / knowledge loss

- Beyond Tenun as a living case

- One or two thought-provoking discussion questions

- Invitation to continue the conversation after the roundtable

## Format / production notes

- Use the same master visual system; do not create a new mini-brand

## Where it will be used

- Invitation-only leaders roundtable during / around TBN Conference

IMPORTANT The roundtable is not a sales seminar. The material should stimulate dialogue, not dominate it.

# 5.12. Kim Tan / Key Leader Executive Brief

Purpose: Prepare a high-level document for a strategic one-on-one conversation focused on validation, perspective, introductions and possible future support.

## Agency to deliver

- Two-page executive brief

- Optional one-page “The Ask” insert

- Digital PDF and print-ready PDF

## Content / message direction

- Page 1: the idea - Humanizing AI → Ancestral Intelligence → Human Flourishing; Beyond Tenun as living case

- Page 2: why we value your perspective - what would make the model credible/fundable, who should join the ecosystem, how it could scale beyond Indonesia

- Clear invitation: help us sharpen, connect and scale the idea

## Format / production notes

- Very premium and minimal; not a repackaged investor deck

## Where it will be used

- One-on-one with Kim Tan

- Other high-level strategic leaders as appropriate

IMPORTANT The first ask should be strategic engagement, not a blunt funding request.

# 5.13. Lead Capture / QR Experience

Purpose: Turn booth and meeting interest into qualified follow-up leads.

## Agency to deliver

- Simple mobile-friendly form / landing page

- QR code asset for booth and printed materials

- Basic lead database/export structure

- Thank-you / confirmation screen

## Content / message direction

- Interest options: Impact Partnership; Foundation / Grant; Philanthropic Capital; Corporate Partnership; Technology Partnership; Education Partnership; Knowledge/Research; Community Visit; Request a Meeting

- Capture: name, organization, role, email/WhatsApp

- After submit: thank-you message + access to executive brief or short deck

## Format / production notes

- Fast to load, low-friction and mobile-friendly

## Where it will be used

- Booth

- Roundtable

- Investor meetings

- Printed one-pagers

# 5.14. Post-Conference Follow-Up Pack

Purpose: Help the team continue conversations quickly after the conference and convert interest into meetings.

## Agency to deliver

- Thank-you visual / cover

- Follow-up message template

- Lightweight short-deck PDF

- Executive one-pager

- Impact Partnership one-pager

- Meeting CTA panel / graphic

## Content / message direction

- Consistent tone: thank you → relevance → one clear next step

- Modular enough for investor, foundation, corporate or technology partner follow-up

## Format / production notes

- Digital-first; WhatsApp/email friendly

## Where it will be used

- Within 24-72 hours after qualified conference conversations

IMPORTANT The conference creates leads. Funding will usually come from the follow-up process; this kit must be ready before the conference starts.

# 6. Production & Handover Requirements

- All deliverables must use the approved master visual and message system.

- Provide final export files plus editable/source files for decks, layouts and graphics wherever technically possible.

- Print materials must be supplied in print-ready format with bleed/safe area according to final vendor specifications.

- Videos must include a 16:9 HD version and a compressed digital-sharing version.

- All content must be reviewed and approved by the ICM/TBN/Torajamelo team before final production.

- Agency must not invent impact figures, beneficiary numbers, investor returns or unapproved claims.

- Any third-party photography, music, fonts or footage must have proper usage rights.

- Agency should use real community/program assets supplied by the team where appropriate, with respectful and non-extractive storytelling.

# 7. Priority Tasks

CORE FOCUS Quality is more important than quantity. If the full scope exceeds budget, prioritize the ten core deliverables below and build the remaining materials from the same templates.

1. Master Key Visual & Message System

2. Main Investor / Impact Partner Pitch Deck

3. Short Investor / Conversation Deck

4. Beyond Tenun Pitch Video

5. ICM Ecosystem Launch / Profile Video

6. Beyond Tenun Executive One-Pager

7. Impact Partnership / Funding One-Pager

8. Booth Master Visual & Environmental Design

9. Booth Screen Content Loop

10. Traceable Weaver Experience / Prototype

The Leaders Roundtable Kit, Kim Tan Brief, Lead Capture and Follow-Up Pack should then be produced efficiently by reusing the master visual system, approved templates and core content.

# 8. Success Standard

THE AGENCY ASSIGNMENT IS SUCCESSFUL WHEN The right people stop, understand the idea, remember Beyond Tenun, ask meaningful questions, and leave the conference wanting a serious next conversation about joining the three-year Impact Partnership.

BEYOND TENUN - SEED TO LOOM

Humanizing Artificial Intelligence through Ancestral Intelligence

From local resilience to human flourishing.